## Sprint Metrics
Sprint Number | Committed Points | Completed Points | Carried Over Points | Bug Tickets Fixed | Dev Hours Logged
Sprint 24 | 180 | 165 | 15 | 24 | 720
Sprint 25 | 185 | 180 | 5 | 18 | 740
Sprint 26 | 190 | 192 | 0 | 12 | 750
Sprint 27 | 195 | 175 | 20 | 30 | 710
Sprint 28 | 200 | 205 | 0 | 14 | 780
Sprint 29 | 210 | 202 | 8 | 22 | 765
Average Summary

## Product Roadmap
Feature/Epic Name | Priority | Development Squad | Status | Target Release | Percent Complete
Multi-Cloud Kubernetes Deployment | High | Infrastructure | In Progress | Q1 2026 | 0.75
High-Throughput Telemetry Pipeline | Critical | Data Platform | In Progress | Q2 2026 | 0.4
Autonomous Pathing Collision Avoidance | High | Robotics AI | Planning | Q3 2026 | 0.15
Edge Compute Fleet Controller v2 | Medium | Embedded Systems | Backlog | Q4 2026 | 0
Customer Portal Metrics Dashboard | Low | Frontend UX | QA Verification | Q1 2026 | 0.95